## Sheet1
week 1 | documentatie | ontwerp character/maps | eisen/functies
week 2 | ontwerp character | begin in unity | mappen implementeren | levels bouwen | thema
week 3 | ontwerp character | levels bouwen | begin enemy | animaties
week 4 | character kleuren | enemy fine tunenen | menu's
week 5 | character implementeren | cutscene | text | visual effect
week 6 | test | sound effect | voice lines
week 7 | fine tunen
week 8 | klaar!!!